## プロジェクト管理
カテゴリ | 工程 | タスク | 担当会社 | 担当者名 | 担当者2 | 開始日 | 終了日 | ステータス | 進捗率 | 備考
| 設計 | 全体システム構成 | mediba | 鈴木 | 原 | 26/3/1 | 26/3/15 | 対応中 | 100% | 英語版・後続作業としてデータ連携設計の影響で修正が必要
|  | インフラ設計 | mediba | 鈴木 | 原 | 26/3/1 | 26/3/15 | 対応中 | 100%
|  | インフラ修正 | mediba | 鈴木 | 原 | 26/3/23 | 26/3/24 | 未着手 | 0%
|  | 画面設計 | mediba | 鈴木 | 原 | 26/3/1 | 26/3/24 | 対応中 | 30% | 遅くとも3/20、できれば今すぐFigmaが欲しい
|  | データ連携設計 | mediba | 鈴木 | 原 | 26/3/1 | 26/3/24 | 対応中 | 30% | 遅くとも3/20、できれば今すぐデータ仕様が欲しい
|  | 広告連携設計 | mediba | 鈴木 | 原 | 26/3/15 | 26/3/31 | 未着手 | 0%
| 実装 | インフラ実装（DEV/STG） | mediba | 鈴木 | 原 | 26/3/13 | 26/3/20 | 未着手 | 0%
|  | 画面実装 | mediba | 鈴木 | 原 | 26/3/15 | 26/4/3 | 対応中 | 10%
|  | データ連携（BE/DB）実装 | mediba | 鈴木 | 原 | 26/3/23 | 26/4/3 | 未着手 | 0%
|  | 管理系（microCMS）機能実装 | mediba | 鈴木 | 原 | 26/3/23 | 26/4/3 | 未着手 | 0% | 遅くとも3/20までにCMS費用含め承認降りていること
|  | 広告実装 | mediba | 鈴木 | 原 | 26/3/23 | 26/4/3 | 未着手 | 0%
| 検証 | テスト計画（脆弱性診断・性能試験） | mediba | 鈴木 | 原 | 26/4/1 | 26/4/15 | 未着手 | 0%
|  | テスト計画（受け入れ試験） | mediba | 木村 | 斉藤 |  |  | 未着手 | 0%
|  | 単体テスト（FE） | mediba | 鈴木 | 原 | 26/3/23 | 26/4/3 | 未着手 | 0%
|  | 内部結合テスト（FE） | mediba | 鈴木 | 原 | 26/3/23 | 26/4/3 | 未着手 | 0%
|  | 単体テスト（BE/CMS） | mediba | 鈴木 | 原 | 26/3/23 | 26/4/3 | 未着手 | 0%
|  | 内部結合テスト（BE/CMS） | mediba | 鈴木 | 原 | 26/3/23 | 26/4/3 | 未着手 | 0%
|  | 外部結合テスト | mediba | 鈴木 | 原 | 26/4/6 | 26/4/10 | 未着手 | 0%
|  | 総合テスト | mediba | 鈴木 | 原 | 26/4/6 | 26/4/10 | 未着手 | 0%
|  | 受け入れ試験 | mediba | 木村 | 斉藤 | 26/4/13 | 26/4/21 | 未着手 | 0% | 品管調整とかできている前提
|  | ブックリスタ試験 | ブックリスタ |  | ???? |  | 26/4/21 | 未着手 | 0% | ここより前にブックリスタ側の作業完了が必要
|  | 脆弱性診断 | mediba | 鈴木 | 原 | 26/4/16 | 26/4/26 | 未着手 | 0%
|  | 性能試験 | mediba | 鈴木 | 原 | 26/4/16 | 26/4/26 | 未着手 | 0%
| 社内手続き | S-in判定会 | mediba | 鈴木 | 原 | 26/4/24 | 26/4/24 | 未着手 | 0%
| リリース | STGリリース | mediba | 鈴木 | 原 | 26/4/6 | 26/4/6 | 未着手 | 0% | 受け入れ試験・総合試験用環境
|  | 商用データ調達 | mediba | 木村 | 斉藤 | ??? | 26/4/22 | 未着手 | 0% | データの分割、JSON用意、CMS上でのデータ編集作業
|  | リリース準備 | mediba | 鈴木 | 原 | 26/4/22 | 26/4/23 | 未着手 | 0% | リリースに向けた手順作成等、ペトリンク作業
|  | PRDリリース（IP閉塞） | mediba | 鈴木 | 原 | 26/4/10 | 26/4/10 | 未着手 | 0% | 脆弱性試験・性能試験機能試験用環境
|  | PRDリリース（IP穴あけ） | mediba | 鈴木 | 原 | 26/4/27 | 26/4/27 | 未着手 | 0%
|  | PRDリリース（デイリーツールリンク修正） | mediba | 鈴木 | 原 | 26/4/27 | 26/4/27 | 未着手 | 0% | トライアル解放

## Project Schedule
Category | Phase | Task | Company | Owner | Sub-owner | Start Date | End Date | Status | Progress | Notes
| Design | Overall System Architecture | mediba | Suzuki | Hara | 26/3/1 | 26/3/15 | In Progress | 100% | English version - needs revision due to impact on data integration design as follow-up work
|  | Infrastructure Design | mediba | Suzuki | Hara | 26/3/1 | 26/3/15 | In Progress | 100%
|  | Infrastructure Revision | mediba | Suzuki | Hara | 26/3/23 | 26/3/24 | Not Started | 0%
|  | Screen Design | mediba | Suzuki | Hara | 26/3/1 | 26/3/24 | In Progress | 30% | Need Figma by 3/20 at the latest, preferably ASAP
|  | Data Integration Design | mediba | Suzuki | Hara | 26/3/1 | 26/3/24 | In Progress | 30% | Need data specs by 3/20 at the latest, preferably ASAP
|  | Ad Integration Design | mediba | Suzuki | Hara | 26/3/15 | 26/3/31 | Not Started | 0%
| Implementation | Infrastructure Setup (DEV/STG) | mediba | Suzuki | Hara | 26/3/13 | 26/3/20 | Not Started | 0%
|  | Frontend Implementation | mediba | Suzuki | Hara | 26/3/15 | 26/4/3 | In Progress | 10%
|  | Data Integration (BE/DB) Implementation | mediba | Suzuki | Hara | 26/3/23 | 26/4/3 | Not Started | 0%
|  | Admin (microCMS) Feature Implementation | mediba | Suzuki | Hara | 26/3/23 | 26/4/3 | Not Started | CMS cost approval must be obtained by 3/20 at the latest
|  | Ad Implementation | mediba | Suzuki | Hara | 26/3/23 | 26/4/3 | Not Started | 0%
| Testing | Test Plan (Vulnerability & Performance) | mediba | Suzuki | Hara | 26/4/1 | 26/4/15 | Not Started | 0%
|  | Test Plan (Acceptance Testing) | mediba | Kimura | Saito |  |  | Not Started | 0%
|  | Unit Test (FE) | mediba | Suzuki | Hara | 26/3/23 | 26/4/3 | Not Started | 0%
|  | Integration Test (FE) | mediba | Suzuki | Hara | 26/3/23 | 26/4/3 | Not Started | 0%
|  | Unit Test (BE/CMS) | mediba | Suzuki | Hara | 26/3/23 | 26/4/3 | Not Started | 0%
|  | Integration Test (BE/CMS) | mediba | Suzuki | Hara | 26/3/23 | 26/4/3 | Not Started | 0%
|  | External Integration Test | mediba | Suzuki | Hara | 26/4/6 | 26/4/10 | Not Started | 0%
|  | System Test | mediba | Suzuki | Hara | 26/4/6 | 26/4/10 | Not Started | 0%
|  | Acceptance Test | mediba | Kimura | Saito | 26/4/13 | 26/4/21 | Not Started | 0% | Assumes QA coordination is already in place
|  | Booklista Test | Booklista |  | ???? |  | 26/4/21 | Not Started | 0% | Booklista side work must be completed before this
|  | Vulnerability Assessment | mediba | Suzuki | Hara | 26/4/16 | 26/4/26 | Not Started | 0%
|  | Performance Test | mediba | Suzuki | Hara | 26/4/16 | 26/4/26 | Not Started | 0%
| Internal Process | S-in Review Meeting | mediba | Suzuki | Hara | 26/4/24 | 26/4/24 | Not Started | 0%
| Release | STG Release | mediba | Suzuki | Hara | 26/4/6 | 26/4/6 | Not Started | 0% | Environment for acceptance & system testing
|  | Production Data Procurement | mediba | Kimura | Saito | ??? | 26/4/22 | Not Started | 0% | Data splitting, JSON preparation, data editing on CMS
|  | Release Preparation | mediba | Suzuki | Hara | 26/4/22 | 26/4/23 | Not Started | 0% | Procedure documentation, Petlink tasks for release
|  | PRD Release (IP Blocked) | mediba | Suzuki | Hara | 26/4/10 | 26/4/10 | Not Started | 0% | Environment for vulnerability, performance & functional testing
|  | PRD Release (IP Unblocked) | mediba | Suzuki | Hara | 26/4/27 | 26/4/27 | Not Started | 0%
|  | PRD Release (Daily Tool Link Fix) | mediba | Suzuki | Hara | 26/4/27 | 26/4/27 | Not Started | 0% | Trial release